## Instructions
Version: v1
INTRODUCTION
The business case template is part of a decision-making tool that helps the District of Summerland prioritize capital projects. The template will help you provide decision-makers with the information needed to assess and decide whether and when a project should get done. The template is part of a clear, consistent, fair and open process everyone follows. It gives all of us a better understanding of the District's needs and will result in an easier and faster budgeting process.
The business case is part of the Project Prioritization Gating Process, which helps the District develop capital projects for prioritization and eventual approval as part of the District budgeting process. Projects will go through the following stage gates during the process:
| Business Case Development Process |  |  | Prioritization Process |  | Budget Process
| GATE 1 Initial Business Case |  | GATE 2 Expanded Business Case | GATE 3 Project Criteria Review | GATE 4 Prioritized List of Projects | GATE 5 Budget
| Final Document: |  | Final Document: | Final Document: | Final Document: | Final Document:
| Business Case (Tab 1) |  | Business Case (Tab 2 & 3) | Updated Project Registry | 5 year capital projects List | Budget
| Sign-Off By: |  | Sign-Off By: | Sign-Off By: | Sign-Off By: | Sign-Off By:
| Dept. Manager |  | Dept. Director | All Directors | All Directors + Finance + CAO | Council
| Time Cycle: |  | Time Cycle: | Time Cycle: | Time Cycle: | Time Cycle:
| Any time |  | Quarterly | Yearly (Aug/Sept) | Yearly (Oct/Nov) | Yearly (Dec/Jan)
INSTRUCTIONS - How to fill out the Business Case
Step 1 | Identify a potential project Route 1: Dept. staff (Chief Operators, Foreman) identify required capital works. Route 2: Dept. managers (Managers, Directors) identify initiatives from strategic documentation (e.g. AM Strategies, Asset masterplans, Climate Action Plans, manufacturer operational manuals, etc.)
Step 2 | Determine if the project is under the "Project Size" threshold If the total capital cost of the project is less than (<) $10,000 then you will not need to fill out a business case for the project. (The project will be considered under the department's operating budget.)
Step 3 | Fill out Tab 1 - Project Description (Dept. Staff - Fill out Tab 1 ONLY) Confirm the Fiscal Year and Fund at the top of the page are correct 1.1 Project Summary (fill out for all project sizes) - Provides general information about the project - The selection in 1.1.9 Project Size will determine which sections are required to be filled out in the rest of the document, look for directions for S, M, L, XL Project sizes, sections that are not required to be filled in will be greyed out 1.2 Project Rationale, Benefits and Considerations (fill out for all project sizes) - Describes the reasons why the project needs to be completed and important information about the project - The selection in 1.2.1 Project Rationale will determine which Project Rationale Criteria (3.1) are required to be filled out in Tab 3 - Input Matrix, sections that are not required to be filled in will be greyed out 1.3 Project Status (fill out for all project sizes) - Details business case contributors and project status and approvals, only authorized decision-makers to change status
Dept. Staff - Once the Project Description is complete and ready for review by the Dept. Manager go to 1.3.2.b Project Description Complete? and select 'Yes'
Dept. Managers - Once the Project Description has been reviewed and revised go to 1.3.2.c Project Description (GATE 1) Approval, select 'Yes' and enter the approvers name
STAGE GATE 1 COMPLETE
Step 4 | Fill out Tab 2 - Fin & Res Analysis (Dept. Managers/Directors - Fill out for all projects) [Sections that are not required to be filled in will be greyed out] 2.1 Financial Analysis - Provides financial information about the project to assist in budgeting and assessment of financial impact to the District 2.1.1 Life-Cycle Financial Impact (fill out for all project sizes) 2.1.2 Asset Renewal Information (fill out for M, L, XL project sizes) 2.1 Resource Analysis - Describes the short and long-term resourcing impacts of the project to the District 2.1.1 Level of Impact to Internal Resources (fill out for all project sizes) 2.1.2 Internal Resourcing Impacts Description (fill out for M, L, XL project sizes)
Step 5 | Fill out Tab 3 - Input Matrix (Dept. Managers/Directors - Fill out for all projects) [Sections that are not required to be filled in will be greyed out] 3.1 Project Rationale Criteria (fill out for all project sizes) - Evaluates the project on its primary benefit - Choose and make a selection for ONLY ONE CRITERIA (all parts) unless the Project truly provides multiple primary benefits (i.e. one project designed to solve two problems) 3.2 Common Criteria (fill out for all project sizes) - Evaluates the project on a range of common benefits or impacts the project may have - Make a selection for ALL CRITERIA (all parts) 3.3 Supplemental Criteria (fill out for all project sizes) - Evaluates the project on a range of additional criteria - Make a selection for ALL CRITERIA (all parts)
Step 6 (OPTIONAL) | Fill out Tab 4 - Suppl. Info (Optional) [Sections that are not required to be filled in will be greyed out] 4.1 Additional Details (Optional - all project sizes) - Provides additional details to the answers provided in 1.2 Project Rationale, Benefits and Considerations 4.2 Other Considerations (Optional - all project sizes) - Describes broader organizational and community considerations and risks associated with the project 4.3 Needs Identification (Optional - M, L, XL Only) - Describes the reasons why the project needs to be completed 4.4 Data & Evidence (Optional - M, L, XL Only) - Describes the information used to analyze and required to complete the project 4.5 Supplemental Analyses (Optional - L & XL ONLY) - Option to provide links to supplemental analyses for the project
Step 7 (OPTIONAL) | Fill out Tab 5 - Options Analysis (Optional) [Sections that are not required to be filled in will be greyed out] 5.1 Preferred Option (Optional - L, XL Projects ONLY) - Selection of the project option to be assessed in the business case 5.2 Option 1 Analysis (Optional - L, XL Projects ONLY) - Provides a description, financial analysis and resource analysis of a potential project option 5.3 Option 2 Analysis (Optional - L, XL Projects ONLY) - Provides a description, financial analysis and resource analysis of a potential project option 5.4 Option 3 Analysis (Optional - L, XL Projects ONLY) - Provides a description, financial analysis and resource analysis of a potential project option
Dept. Managers - Once the Business Case is complete go to 1.3.2.d Business Case Complete? and select 'Yes'
Directors - Once the Business Case has been reviewed and revised go to 1.3.2.e Business Case (GATE 2) Approval, select 'Yes' and enter the approvers name. This review process includes encorporating feedback from other departments with respect to collaboration oppurtunities.
STAGE GATE 2 COMPLETE
Directors - Once the Business Case Input Matrix selections have been validated by all Dept. Directors following the group criteria review meeting in September/ October, the business case is ready to be input into the prioritization model. Go to 1.3.2.f Criteria Selection Review (GATE 3) Approval? and select 'Yes'
NOTE: This will result in the business case being moved to the prioritization folder, and will be included in the initial prioritized list for evaluation by all Dept. Directors, Finance, and the CAO.
STAGE GATE 3 COMPLETE
Directors - If at any time the project is no longer being pursued OR the project has been approved, budgeted, and moved to design phase go to 1.3.3 Business Case Status and update its status
NOTE: Selecting 'Archived' will cause the project to be removed from the prioritization projects list and the prioritization model inputs and outputs. Only select 'Budgeted' once the project has been through all project stage gates and has been approved and budgeted. This will be used for recording-keeping purposes only.
Business Case - Capital Projects
How to fillout Business Case Input Sheet (Draft 1)
Input fields are in green and tan color boxes.
1) Use this sheet for Small Projects only (10K to 25K). Other business case input sheets are available for other size projects.
2) Start by filling out the fields in '1 - Description' tab
3) Next fill out the '2 - Supplemental Info' tab
4) Finally fill out the '3 - Options Analysis' tab
Project Size
S = 10K to 25K
M = 25.1K to 100K
L = 100.1K to 500K
XL = 500.1K

## 1 - Project Description
Legend:
|  |  |  | FISCAL YR: | 2022 |  | Drop down list
|  |  |  | FUND: | General |  | Open text field
Version: v1
1.0 PROJECT DESCRIPTION |  |  | Dept. Staff - Fill Out Tab 1 ONLY
1.1 Project Summary
1.1.1 Project File Name |  |  | Project File Name: | FILL IN 1.1.1.a
Format: [Fiscal Year]-[Fund]-[Dept(if appl)]-[Short_Proj_Name]
|  |  | File Name Check: | 2021-Water_BusCase_Template
| 1.1.1.a Short Project Name (25 character maximum, must be unique) |  | unique_proj_name |  | Text
1.1.2 Project Name |  |  | Name of project - Should be reasonably short and descriptive
1.1.3 Project Description
| 1.1.3.a Purpose of the Project |  | Briefly describe the main problem that the project is intended to solve.
| 1.1.3.b Brief Project Description |  | Describe the work to be completed in no more than three sentences
1.1.4 Department (for General Fund only) |  |  | N/A |  | Select from drop down list
(Department where funds for the Project are to be allocated from)
1.1.5 Project Contact |  |  | Name of primary contact for project information |  |  | Text
1.1.6 Project Location(s) |  |  | Street number and name or other relevant map reference. For linear projects identify starting and ending locations. For projects with multiple locations specify 'multiple' and provide link to supporting documentation |  |  |  | Text
1.1.7 Project Start Date
| 1.1.7.a Planned Start Date |  | 2021-01-01 | mmm-yyyy
| 1.1.7.b Timing Constraints or Limitations |  | Note any constraints or limitations that may prevent this project from being started at a different time. If there are no constraints or limitations specify "None". |  |  |  | Text
1.1.8 Project Duration |  |  |  | # of months (must be <60)
1.1.9 Project Size |  |  | Small (S) Total capital costs of project are: greater than or equal to $10,000 and less than $50,000 | Medium (M) Total capital costs of project are: greater than or equal to $50,000 and less than $250,000 | Large (L) Total capital costs of project are: greater than or equal to $250,000 and less than $750,000 | Extra Large (XL) Total capital costs of project are: greater than $750,000
(Project Size is determined by the total capital costs of the project. If the project capital costs are less than $10,000 the project will be considered an operational expense and no business case needs to be completed.)
Select from drop down list
CROSS-CHECK (For Gate 2 - Dept. Managers or Directors ONLY) |  |  |  |  | Total CAPEX - Project Costs from Section 2.1.1.a (Tab 2): | 0
[5 empty] | Expected Project Size based on Financial Analysis: | NO BUS. CASE NEEDED
1.2 Project Rationale, Benefits and Considerations
1.2.1 Project Rationale |  |  | Improve or Increase LOS Project will deliver a sustained customer service improvement. Levels of service (LOS) will increase from current state. | Maintain or Restore LOS - Same Capacity Project will maintain existing asset reliability (i.e. avoidance of failure) AND/OR Project will maintain service performance (i.e. avoidance of service degredation) (e.g. extend useful life, refurbish/replace as required). | Increase Capacity and/or Growth Project will increase capacity to meet forecast demand OR Project meets an immediate need due to development approval at the same LOS (This may include climate change adaptation requiring an increased asset capacity to maintain existing LOS)
(i.e. what is the primary benefit of the project, or the main reason or purpose for the project?) *If the main purpose of the project is to decomission an asset, select Maintain/Restore LOS - Same Capacity
Select from drop down list
1.2.2 Sustainability Co-Benefits (Select all that apply) |  |  |  | Improved Biodiversity |  | Select from drop down list
| (i.e. what are the expected additional or non-primary benefits (direct and indirect) of the project to the organization and/or the community?) |  |  | Improved Water Retention/Absorption |  | Select from drop down list
|  |  |  | Pollutant Capture |  | Select from drop down list
|  |  |  | Reduced Extreme Temperatures |  | Select from drop down list
|  |  |  | Job Creation |  | Select from drop down list
|  |  |  | Energy Savings |  | Select from drop down list
|  |  |  | Reduced Waste |  | Select from drop down list
|  |  |  | Increased Local Control of Energy |  | Select from drop down list
|  |  |  | Increased Property Values |  | Select from drop down list
|  |  |  | Reduced Road Congestion |  | Select from drop down list
|  |  |  | Other (specify below) |  | Select from drop down list
|  |  |  | Enter other here: |  | Text
*If further explanation is needed, use 1.2.8 below.
1.2.3 Can the Project be Grant Funded? |  |  | Unknown | Select from drop down list
| (i.e., Can the District access external funds to pay for all or part of the project?) |  |  | If 'Yes' you may go to "4 - Suppl. Info (Optional)" tab and fill out additional information in Section 4.1.1
1.2.4 Are There Project Interdependencies? |  |  | Unknown | Select from drop down list
| (i.e., impacts, positively or negatively, other department's operations, other assets, or other services, or presents opportunities for collaboration, corridor optimization, or similar) |  |  | If 'Yes' you may go to "4 - Suppl. Info (Optional)" tab and fill out additional information in Section 4.1.2
1.2.5 Does the Project Support a Current Strategic Initiative? |  |  | Unknown | Select from drop down list
| (i.e., Is the project executing or aligned with a current District council priority, master plan, or similar?) |  |  | If 'Yes' you may go to "4 - Suppl. Info (Optional)" tab and fill out additional information in Section 4.1.3
1.2.6 Is the Project Replacing an Existing Asset? |  |  | Unknown | Select from drop down list
| (Is the primary purpose of the project to renew an asset, i.e., to refurbish, replace or significantly upgrade the asset?) |  |  | If 'Yes' you may go to "4 - Suppl. Info (Optional)" tab and fill out additional information in Section 4.1.4
1.2.7 Does the Project have Ecological Impacts? |  |  | Unknown | Select from drop down list
| (i.e., impacts, positively or negatively, the air, water, soil, vegetation, wildlife, or other ecological characteristics of the local environment) |  |  | If 'Positive (+)', 'Negative (-)', or 'Mixed (+ & -)' you may go to "4 - Suppl. Info (Optional)" tab and fill out additional information in Section 4.1.5
1.2.8 Other Important Information |  |  | Describe any other important information that has not been disclosed that you feel should be considered in assessing the project |  |  |  | Text
1.3 Project Status
1.3.1 Business Case Contributor(s) |  |  | List all staff, managers, directors or others who have substantively contributed to the development of this business case |  |  |  | Text
1.3.2 Project Status and Approvals
| 1.3.2.a Project Status |  |  | Project Status: | Project Description Incomplete
| 1.3.2.b Project Description Complete? |  | No | Select from drop down list | Date completed: |  | dd-mmm-yyyy
| (All mandatory fields in Sections 1.1 and 1.2 have been filled in) |  | Project description is complete and is ready to be reviewed by department manager
|  |  |  | Timeline: | Ongoing, can be completed at any time
|  |  |  | Authorized Decision-Maker(s): | Chief Operator, Foreman, Dept. Manager, Director
| 1.3.2.c Project Description (GATE 1) Approval |  | No | Select from drop down list | Date approved: |  | dd-mmm-yyyy
| (Completed project description has been reviewed, revised, and approved by an authorized approver) |  |  |  | Approved by: | Name
|  |  |  | Timeline: | Ongoing, can be completed at any time, minimum quarterly
|  |  |  | Authorized Approver(s): | Dept. Manager, Director
STAGE GATE 1 COMPLETE
| 1.3.2.d Business Case Complete? |  | No | Select from drop down list | Date completed: |  | dd-mmm-yyyy
| (Project description is complete - see Section 1.3.1.b - AND all mandatory fields in Tab "2 - Fin & Res Analysis" and Tab "3 - Input Matrix" have been filled in) |  | Business case has been completed by department manager and is ready to be reviewed by department director
|  |  |  | Timeline: | Ongoing business case completion, quarterly review and approval
|  |  |  | Authorized Decision-Maker(s): | Dept. Manager, Director
| 1.3.2.e Business Case (GATE 2) Approval |  | No | Select from drop down list | Date approved: |  | dd-mmm-yyyy
| (Completed business case has been reviewed, revised, and approved by an authorized approver, following a quarterly collaboration review meeting) |  |  |  | Approved by: | Name
|  |  |  | Timeline: | quarterly
|  |  |  | Authorized Approver(s): | Director
STAGE GATE 2 COMPLETE
| 1.3.2.f Criteria Selections Review (GATE 3) Approval? |  | No | Select from drop down list | Date ready: |  | dd-mmm-yyyy
| (Business Case Input Matrix selections have been reviewed, revised, and approved by all authorized approvers during the group criteria review) READY TO MOVE TO GATE 4 |  | Business case is ready to move into prioritization process and be prioritized for current year budgeting
|  |  |  | Timeline: | Yearly selection for prioritization process (August/September)
|  |  |  | Authorized Decision-Maker(s): | All Directors
STAGE GATE 3 COMPLETE, READY TO MOVE TO STAGE GATE 4
1.3.3 Business Case Status
| Describes the status of the Business Case, used for determining whether the Business Case is part of the current prioritization process or not. |  | Active | Select from drop down list | Date archived: |  | dd-mmm-yyyy
Project is no longer being pursued (select 'Archived') OR Project has been approved, budgeted, and moved to design phase (select 'Budgeted')
|  |  |  | Timeline: | Ongoing OR yearly, post-budget approval
|  |  |  | Authorized Decision-Maker(s): | Director
Business Case - Capital Projects
Note on J50: The project increases the number and variety of plants and animals and/or creates space that allows for the increase in existing plant and animal communities (e.g. expanding greenspaces to improve habitat connection; increasing available space for local plants and animals).
Note on J51: The project minimizes the impacts of heavy rainfall by increasing permeable surfaces that retain and absorb excess water, allowing for groundwater recharge and reducing loads on stormwater infrastructure (e.g. “living” infrastructure like green roofs/walls, raingardens, trees, swales, and permeable pavements that reduce runoff and absorb rainfall from nearby roads and rooftops).
Note on J52: The project reduces pollution before it enters the environment (water, land, or air) or treats pollutants using engineered or biological means (e.g. incorporating wetlands and roadside vegetation can absorb vehicle and roadway pollutants; using scrubbers and ventilation systems in buildings to trap pollutants at their sources).
Note on J53: The project includes measures to moderate impacts from extreme heat (e.g. highly reflective roofs help reduce extreme heat; site vegetation and greenspaces provide shading and evaporative cooling during hot weather and windbreaks during cold weather).
Note on J54: The project will increase temporary or full-time employment and/or training opportunities through construction, maintenance/operations, and/or economic spin-offs (e.g., new jobs or roles within organizations; retraining and expanding roles; improves viability to other local businesses).
Note on J55: The project reduces energy consumption, improves energy efficiency, or uses alternative renewable energy sources (e.g. using passive heating/cooling or other low energy design; retrofits with best available technology, such as LEDs, draft-proofing, heat pumps, solar hot water.
Note on J56: The project will divert waste from landfill and/or encourage the reuse of material/energy (e.g. salvaged materials will be reused in another project; purchased materials are made of recycled materials and/or can be fully recycled; recovering heat energy from sewage treatment processes and other facilities).
Note on J57: The project increases the District’s ability to anticipate and respond to changing local conditions, through policy and public/private collaboration (e.g. greater control over decisions related to energy, infrastructure, emergency responses, etc.; improved community partnership networks).
Note on J58: The project minimizes hazards associated with risks such as flooding, wildfire, or drought; and/or increases the value of property by expanding adjacent green space (e.g. use of green infrastructure, stilts, or sump pumps in flood-prone areas; fire resistant materials in fire-prone areas; green spaces on/near properties).
Note on J59: The project reduces the number of vehicles on the road per capita (e.g. increasing density; restricting parking; designing effective walkway and bikeway policy and infrastructure; ride-sharing programming to minimize single occupant vehicle use).

## 2 - Fin & Res Analysis
Legend:
[8 empty] | FISCAL YR: | 2022 | [5 empty] | Drop down list
[8 empty] | FUND: | General | [5 empty] | Open text field
Version: v1 | [15 empty] | 0
2.0 FINANCIAL AND RESOURCE ANALYSIS
2.1 Financial Analysis
2.1.1 Life-Cycle Financial Impact |  |  |  | (FILL OUT FOR ALL PROJECTS) |  |  | NOTE: The Total Financial Cost or Return (Net Present Cost) amount will determine the selection made for 3.2.4 Life Cycle Financial Impact criteria under Tab '3 - Input Matrix'
Fill out only those that apply
| * | Sec. # | Description |  |  | Net Present Cost** |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041
|  |  | (estimate the difference from before project to after project) |  |  | ("NPC") | bar: 2022 to 2041
| + | 2.1.1.a | CAPEX - Project Costs (purchase/engineering/construction costs, incl. resourcing) |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - | 2.1.1.b | CAPEX - Expected External Funding for Project |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 2.1.1.c | CAPEX - Change in Major Maintenance / Life-Cycle Activities Costs*** |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 2.1.1.d | OPEX - New Revenues From Project / Reduction of Service Revenues |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 2.1.1.e | OPEX - Change in Regular Operating and Maintenance Costs**** |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL FINANCIAL COST (RETURN) |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| * | Increase in costs OR decrease in revenues = Positive $ amount (+) Decrease in costs (i.e. cost savings) OR increase in revenues = Negative $ amount (-) | [5 empty] | 2022: Project Size does not match CAPEX - Project Costs
| ** | Assumes Yr 1 is current year
| *** | Change in costs to conduct major maintenance, or to refurbish, replace or upgrade the asset related to the project, including renewal or major maintenance periods. These are maintenance projects >$10,000 which should be noted as CAPEX not OPEX. If this project is for a new asset, the future lifecycle costs associated with this asset will be entered into this row as a (+) value. If this project involves an existing asset, future lifecycle costs will be entered as a (+) value in the year they are expected to occur if the project is completed. Future lifecycle costs will be entered as a (-) value in the year they would have been incurred if the project is not completed. See training notes for further explanation.
| **** | Including change in risk costs (cost of reasonably expected major adverse event @ expected frequency of occurance) and other avoided costs (fines, penalties, fees, or any other one-off costs not already captured)
2.1.1.f Additional Information on Lifecycle Financial Impacts |  |  |  | Add Comments |  |  |  | 2026: Text
Use this section to provide justification for inputs in the financial impacts table. This may include an explanation of change in major maintanance activities, assumptions made in the change in revenues or change in OPEX, links to supporting documentation, or any other comments relavent to others who will review the project. | bar: 2022 to 2025
2.1.2 Asset Inventory Information |  |  |  | (FILL OUT ONLY FOR M, L, XL Projects)
| 2.1.2.a Is this a new asset? |  |  | Does this project create a net new asset where there was not one before? Select 'Yes' if any of the assets involved in the project are net new.
Select from drop down list
| 2.1.2.b Expected Useful Life of Related Asset (if applicable) |  |  | If applicable, estimate the expected total useful life the related asset (i.e. how often will it need to be renewed)
|  |  |  | 0 | Period (in Years)
| 2.1.2.c Estimated Remaining Useful Life of Related Asset (if applicable) |  |  | If applicable, estimate the remaining useful life of the related asset (must be less than 2.1.2.b)
|  |  |  | 0 | (in Years)
2.2 Internal Resource Analysis
2.2.1 Level of Impact to Internal Resources |  |  |  | (FILL OUT FOR ALL PROJECTS)
| (Impact to Internal Resources ONLY. External staff and equipment costs for the project are accounted for as part of Project Costs (see Section 2.1.1.a). Net new internal staff or equipment needed for the project will to be accounted for as part of Project Costs as well, but will also be considered in this section.) |  |  | 1 - Insignificant Minimal short term staff and/or equipment hours required to resource project; No additional ongoing staff and/or equipment hours required as a result of the project |  | 2 - Minor Some short term staff and/or equipment hours required to resource project (covered by capital projects staffing reserves); Minimal additional ongoing staff and/or equipment hours required as a result of the project |  | 2022: 3 - Moderate Significant short term staff and/or equipment hours required to resource project (NOT covered by capital projects staffing reserves); Minimal additional ongoing staff and/or equipment hours required as a result of the project; 2024: 4 - Major New short term staff position required and/or significant equipment hours required to resource project (NOT covered by capital projects staffing reserves); Some additional ongoing staff and/or equipment hours required as a result of the project; 2026: 5 - Severe New staff position and/or new equipment needed to resource continuing O&M as a result of the project
Select from drop down list
2.2.2 Internal Staff and Equipment Resourcing Impacts |  |  |  | (FILL OUT ONLY FOR M, L, XL Projects)
| 2.2.2.a Describe internal staff requirements for design/construction phase, including estimated hours needed by position. (See optional table 2.2.2.e below) |  |  | For example: This project will require 20 hours for the GIS Coordinator to gather data. |  |  |  | 2031: Text
| 2.2.2.b Describe internal equipment/fleet requirements for design/construction phase, including estimated hours needed by equipment type. |  |  | For example: this project will require 100 hours of a large piece of machinery such as an excavator. |  |  |  | 2031: Text
| 2.2.2.c Describe internal staffing impacts for ongoing operations and maintenance, including estimated FTEs required by position. (See optional table 2.2.2.f below) |  |  | For example: A new park may require an additional 2 hours of park maintanance staff time per week for additional mowing. |  |  |  | 2031: Text
| 2.2.2.d Describe internal equipment/fleet impacts for ongoing operations and maintenance, including new equipment needed. |  |  | For example: The new asset will require site inspections every 6 months, and will require an ATV to access. |  |  |  | 2031: Text
| 2.2.2.e (Optional) Detailed breakdown of internal staff requirements for design/ construction phase. |  |  | Department |  | Position |  | 2022: Hourly Rate; 2024: Hours; 2026: Total Cost (Hourly Rate x Hours)
Note that this table is to help structure thinking around internal resource costs, however the data is not specifically linked to the financial calculations. These costs should be built into the financial table in section 2.1.1.a. | [7 empty] | 2026: 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Total |  |  |  | 2026: 0
| 2.2.2.f (Optional) Detailed breakdown of internal staff requirements for ongoing operations and maintenance. |  |  | Department |  | Position |  | 2022: Hourly Rate; 2024: Hours; 2026: Total Cost (Hourly Rate x Hours)
Note that this table is to help structure thinking around internal resource costs, however the data is not specifically linked to the financial calculations. These costs should be built into the financial table in section 2.1.1.e. | [7 empty] | 2026: 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Total |  |  |  | 2026: 0
Business Case - Capital Projects

## 3 - Input Matrix
Legend:
|  |  |  | FISCAL YR: | 2022 |  |  | Drop down list
|  |  |  | FUND: | General |  |  | Open text field
Version: v1 |  |  | 0 |  |  |  |  | 0
3.0 INPUT MATRIX
| Decision Criteria | Criteria Description | Scale Description | Scale Level Descriptions
3.1 Project Rationale Criteria (Primary Benefit)
3.1.1 | Improve/Increase LOS | Project will deliver sustained customer service improvement. Levels of service (LOS) will increase from current state. NOTE: Applies to both natural and engineered assets | A) Level of impact | 1 - Insignificant Delivers a sustained increase in LOS that addresses a very minor deviation from expected standards, policy or LOS targets. No record of historical concerns. | 2 - Minor Delivers a sustained increase in LOS that addresses a somewhat minor deviation from expected standards, policy or LOS targets. Determined through studies. Some sporadic history of concerns. | 3 - Moderate Delivers a sustained increase in LOS that addresses a moderate deviation from expected standards, policy or LOS targets. Determined through studies. Some sporadic history of concerns. | 4 - Major Delivers a sustained increase in LOS that addresses a significant deviation from expected standards, policy or LOS targets. Determined primarily through studies. Some intermittent history of concerns. | 5 - Severe Delivers a sustained increase in LOS that addresses a major deviation from expected standards, policy or LOS targets. Determined primarily through studies. History of frequent and significant concerns. | Complete
|  |  | Select from drop down list | NA | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) Breadth of impact (population) | 1 - Less then 10% Affects < 10% of total community population | 2 - 10% to 40% Affects between 10% and 40% of total community population | 3 - 41% to 70% Affects between 41% and 70% of total community population | 4 - Greater then 71% Affects between 71% and 100% of total community population | 5 - All Affects all of the community population
|  |  | Select from drop down list | NA | Comments (Optional): Add comments here if you wish to justify the selection
3.1.2 | Maintain/Restore LOS - Same Capacity | Project will maintain existing asset reliability (i.e. avoidance of failure) AND/OR Project will maintain service performance (i.e. avoidance of service degredation) EXAMPLES: extend useful life of asset, refurbish/replace asset, or similar NOTE: Applies to both natural and engineered assets | A) Consequence Avoided (asset failure / service impairment avoided) | 1 - Insignificant Minor failure or decline in service. Impact is short term and can be mitigated by operational fixes. No inconvenience / potential for user complaint. No associated damage and/or remedial costs. | 2 - Minor Performance failure and/or decline in service. Small but noticeable impact on service. Minor inconvenience / potential for user complaint. Very little associated damage and/or remedial costs. | 3 - Moderate Performance failure and/or decline in service. Moderate impact on service. Significant, but short term inconvenience, likely to lead to user complaints. Potential for some limited associated damage and/or remedial costs. | 4 - Major Performance failure and/or decline in service. Serious impact on service. Significant extended inconvenience, likely to lead to strong user complaints. Potential for significant associated damage and/or remedial costs. | 5 - Severe Prolonged / persistent major failure and/or service deterioration. Major impact on service. Major ongoing inconvenience, likely to lead to strong, broad-based user complaints. Potential for major associated damage and/or very costly remedial measures. | Complete
|  |  | Select from drop down list | NA | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) Likelihood (asset failure / service impairment avoided) | 1 - Rare May only occur in certain conditions Every 10+ years 0% to 10% | 2 - Unlikely Could occur some time Every 5 to 10 years 10% to 40% | 3 - Possible Might occur at some time Every 3 to 5 years 40% to 60% | 4 - Likely Will probably occur in most circumstances Every 2 to 3 years 60% to 90% | 5 - Almost Certain Almost certain to occur Annually or more frequently 90% to 100%
|  |  | Select from drop down list | NA | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | C) Criticality (of Asset / System / Service) | 1 - Very Low Discretionary service for small proportion of community population. Does not impact vulnerable population. | 2 - Low Discretionary service for a limited proportion of community population. Minor impact to vulnerable population. | 3 - Moderate Discretionary service for significant proportion of community population OR Essential service for small proportion of community population. Moderate impact to vulnerable population. | 4 - High Essential service for significant proportion of community population. Major impact to vulnerable population | 5 - Very High Essential service impacting human health for majority of community population
|  |  | Select from drop down list | NA | Comments (Optional): Add comments here if you wish to justify the selection
3.1.3 | Increase Capacity/Growth | Project will increase capacity to meet forecast demand OR Project meets an immediate need due to development approval at the same LOS NOTE: Applies to both natural and engineered assets NOTE: Projects may include climate change adaptation requiring an increased asset capacity to maintain existing LOS | A) Level of need (to meet new growth) | 1 - Very Low Project accommodates growth projected more than 10 years out. | 2 - Low Project accommodates growth projected between 5 to 10 years out. | 3 - Moderate Project accommodates growth projected between 2 to 5 years out. | 4 - High Project accommodates growth projected between 1 to 2 years out. | 5 - Very High Project accommodates current capacity gap or will avoid developers halting work. | Complete
|  |  | Select from drop down list | NA | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) Criticality (of Asset / System / Service) | 1 - Very Low Discretionary service for small proportion of community population. Does not impact vulnerable population. | 2 - Low Discretionary service for a limited proportion of community population. Minor impact to vulnerable population. | 3 - Moderate Discretionary service for significant proportion of community population OR Essential service for small proportion of community population. Moderate impact to vulnerable population. | 4 - High Essential service for significant proportion of community population. Major impact to vulnerable population | 5 - Very High Essential service impacting human health for majority of community population
|  |  | Select from drop down list | NA | Comments (Optional): Add comments here if you wish to justify the selection
3.2 Common Criteria - Fill out all criteria
3.2.1 | Compliance | Project avoids non-compliance AND/OR Project avoids the consequences of non-compliance (i.e. fines, license revocation, imprisonment, etc.). NOTE: May include new or existing requirements | A) Consequence of non-compliance OR addresses new requirements | 1 - Minor Minor breach. OR Addresses new requirements which are currently open to challenge. | 2 - Some Statutory body notification, possibly through regular reporting, but no further action. OR Addresses new requirements which have significant grey areas. | 3 - Moderate Statutory body notification with further external investigation. OR Addresses new requirements which have some degree of certainty. | 4 - Significant Statutory / regulatory intervention, potential for fines. OR Addresses new requirements that are fairly clear. | 5 - Major Major breach, potential for substantial fines and/or imprisonment, potential for revocation of license. OR Addresses new requirements which are certain.
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) Likelihood of non-compliance | 1 - Very Low Very low likelihood of non-compliance | 2 - Low Low likelihood of non-compliance | 3 - Moderate Moderate likelihood of non-compliance | 4 - High High likelihood of non-compliance | 5 - Very High Very High likelihood of non-compliance
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
3.2.2 | Health & Safety Impact | Project avoids the immediate/acute risk of death and/or injury of the population NOTE: Use '3.2.6 Community Benefit - Social / Cultural' to evaluate long-term and/or indirect (public) health impacts, i.e., wellness, mental health, disease prevention, and other similar impacts) | A) Consequence Avoided (injury level avoided) | 1 - Insignificant insignificant injuries / exposure no treatment required | 2 - Minor Minor injury or illness requires medical treatment (reportable time loss injury > 1 day) | 3 - Moderate Serious / significant injury or illness requires hospitalization | 4 - Major Major injury involving permanent disability or illness | 5 - Severe Fatality
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) Likelihood (chance of injury) | 1 - Rare May only occur in certain conditions OR Occurs every 10+ years OR 0% to 10% chance of occurence | 2 - Unlikely Could occur some time OR Occurs every 5 to 10 years OR 10% to 40% chance of occurence | 3 - Possible Might occur at some time OR Occurs every 3 to 5 years OR 40% to 60% chance of occurence | 4 - Likely Will probably occur in most circumstances OR Occurs every 2 to 3 years OR 60% to 90% chance of occurrence | 5 - Almost Certain Almost certain to occur OR Occurs annually or more frequently OR 90% to 100% chance of occurence
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | C) Scale of impact (population effected) | 1 - Less then 1% < 1% of total community population affected | 2 - 1% to 25% 1% to 25% of total community population affected | 3 - 26% to 50% 25% to 50% of total community population affected | 4 - 51% to 75% 50% to 75% of total community population affected | 5 - Greater then 75% 75% to 100% of total community population affected
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
3.2.3 | Resiliency | Project improves resiliency to major adverse events (including climate change) OR Project increases asset / system redundancy, coverage, backup, or hardening OR Project improves monitoring and/or recovery time (i.e. service resiliency) OR Project improves adaptability (i.e., the ability to incorporate best practices and technological improvements) OR Project reduces asset / system vulnerabilities / uncertainties NOTE: Projects must fully consider climate change projections and potential climate change impacts over the full life-cycle of the related asset | A) Improvement in resiliency AND/OR Degree addresses uncertain vulnerability | 1 - Minor Minor improvement in overall asset / system resiliency. Leaves key / urgent concerns in place. AND/OR Minor improvement in redundancy, coverage, backup, or hardening for a few pieces of critical equipment or sub-systems. AND/OR Provides minor improvement to asset or service monitoring and/or restoration times. AND/OR Provides minor improvement in adaptability of asset / system / service / maintenance / operations. AND/OR Addresses an identified vulnerability which has very high degree of uncertainty around assumptions or data. | 2 - Some Some improvement in overall asset / system resiliency. Addresses some lesser concerns, but still leaves many key / urgent concerns in place. AND/OR Some improvement in redundancy, coverage, backup, or hardening for some critical equipment or sub-systems. AND/OR Some improvement to asset or service monitoring and/or restoration times. AND/OR Some improvement in adaptability of asset / system / service / maintenance / operations. AND/OR Addresses a vulnerability which has high degree of uncertainty around assumptions or data. | 3 - Moderate Moderate improvement in overall asset / system resiliency. Partially addresses key/urgent concerns, but still leaves several concerns in place. AND/OR Moderate improvement in redundancy, coverage, backup, or hardening for most critical equipment or sub-systems. AND/OR Moderate improvement to asset or service monitoring and/or restoration times. AND/OR Moderate improvement in adaptability of asset / system / service / maintenance / operations. AND/OR Addresses vulnerability(s) where assumptions are generally considered sound, but there may be some uncertainties. | 4 - Significant Significant improvement in overall asset / system resiliency. Addresses most aspects of key/urgent concerns, but may leave some lesser concerns in place. AND/OR Significant improvement in redundancy, coverage, backup, or hardening for all critical equipment and sub-systems. AND/OR Significant improvement to asset or service monitoring and/or restoration times. AND/OR Significant improvement in adaptability of asset / system / service / maintenance / operations. AND/OR Addresses vulnerability(s) identified through robust analysis, supported by data and other associated evidence. | 5 - Major Major improvement in overall asset / system resiliency. Fully addresses all key/urgent concerns. AND/OR Major improvement in redundancy, coverage, backup, or hardening for all necessary equipment and sub-systems. AND/OR Major improvement to asset or service monitoring and/or restoration times. AND/OR Major improvement in adaptability of asset / system / service / maintenance / operations. AND/OR Addresses vulnerabilities identified through robust analysis and which have concluded the issues addressed are among the most urgent.
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
3.2.4 | Life Cycle Financial Impact* | NPC of: Project Costs External Project Funding Change in Major Maintenance/Life-Cycle Costs Change in Revenues Change in O&M Costs | Range of life cycle financial return/cost (- to +) *See Tab '2 - Fin & Res Analysis' section '2.1.1 Life-Cycle Financial Impact' for inputs and calculations | 1 - Significant Negative (--) This project will result in a cost to the district of greater than $250,000 | 2 - Negative (-) This project will result in a cost to the district of between $10,000 and $250,000 | 3 - Neutral / Break Even This project will result in either a cost or savings of less then $10,000 to the district. | 4 - Positive (+) This project will result in a savings to the district of between $10,000 and $250,000 | 5 - Significant Positive (++) This project will result in a savings to the district of greater than $250,000
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
3.2.5 | Community Benefit - Environmental | Project results in positive or negative impact on environmental conditions (incl. air, water, soil, biome) AND/OR Project increases or reduces the level of natural stock (i.e., urban trees, bodies of water, wetlands, etc.) AND/OR Project results in increased or reduced risk of negative environmental impact (incl. effects of local toxins or pollution), either one-off or over life-cycle. NOTE: Not GHG related, see separate GHG criteria 3.2.8 below | A) Level of impact | 1 - Significant Negative (--) Significant negative environmental impacts expected as a result of project AND/OR Greatly reduced level of natural stock expected as a result of project | 2 - Negative (-) Negative environmental impacts expected as a result of project AND/OR Somewhat reduced level of natural stock expected as a result of project | 3 - No Impact No environmental impacts expected as a result of project AND/OR No change in level of natural stock expected as a result of project | 4 - Positive (+) Positive environmental impacts expected as a result of project AND/OR Somewhat increased level of natural stock expected as a result of project | 5 - Significant Positive (++) Significant positive environmental impacts expected as a result of project AND/OR Greatly reduced level of natural stock expected as a result of project
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) Breadth of impact (geographic area and/or time) | 1 - Minor Affects non-sensitive area or species AND/OR Effects are very localized (specific site) AND/OR Effects last less than 1 year | 2 - Some Affects non-sensitive area or species AND/OR Effects are localized (site and surrounding area) AND/OR Effects last between 1 and 5 years | 3 - Moderate Affects a sensitive area or species AND/OR Effects are moderately wide-spread (Neighborhood-level) AND/OR Effects last between 5 and 10 years | 4 - Significant Affects a sensitive area or species AND/OR Effects are broad (significant proportion of total community footprint) AND/OR Effects last more than 10 years | 5 - Major Affects protected and/or very sensitive area(s) or species AND/OR Effects are very broad (Airshed or Watershed-level or beyond) AND/OR Effects are permanent and irreversible
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
3.2.6 | Community Benefit - Social / Cultural | Project results in positive or negative impact to community population's physical health (i.e. public health outcomes) AND/OR Project results in positive or negative impact to community population's "wellness", including psychological wellness (i.e. community satisfaction, "happiness", social cohesion, trust), actual and perceived crime/safety, inequality, access to social supports / safety nets, and social outcomes AND/OR Project results in increased or reduced risk of negative social impact, either one-off or on an ongoing basis OR Project results in increased or decreased availability or access to cultural events and the arts | A) Level of impact | 1 - Significant Negative (--) Significant negative impacts to ongoing public health, wellness, social outcomes, or culture expected as a result of project | 2 - Negative (-) Some negative impacts to ongoing public health, wellness, social outcomes, or culture expected as a result of project | 3 - No Impact No impacts to ongoing public health, wellness, social outcomes, or culture expected as a result of project | 4 - Positive (+) Some positive impacts to ongoing public health, wellness, social outcomes, or culture expected as a result of project | 5 - Significant Positive (++) Significant positive impacts to ongoing public health, wellness, social outcomes, or culture expected as a result of project
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) Breadth of impact (population) | 1 - Less than 1% < 1% of total community population affected OR No effect on vulnerable population(s) | 2 - 1% to 25% 1% to 25% of total community population affected OR Limited effect on vulnerable population(s) | 3 - 26% to 50% 26% to 50% of total community population affected OR Moderate effect on vulnerable population(s) | 4 - 51% to 75% 51% to 75% of total community population affected OR significant effect on vulnerable population(s) | 5 - Greater than 76% Greater then 76% of total community population affected OR Major effect on vulnerable population(s)
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
3.2.7 | Community Benefit - Economic | Project results in positive or negative impact to local economy (i.e. # of businesses, # of jobs, productivity, tourism, etc.) AND/OR Project results in improved or reduced economic resiliency (i.e. industry diversity, # of businesses, business health) AND/OR Project results in increased or reduced risk of negative economic impact, either one-off or on an ongoing basis | A) level of impact | 1 - Significant Negative (--) Significant negative impacts to local economy expected as a result of project | 2 - Negative (-) Negative impacts to local economy expected as a result of project | 3 - No Impact No impacts to local economy expected as a result of project | 4 - Positive (+) Positive impacts to local economy expected as a result of project | 5 - Significant Positive (++) Significant positive impacts to local economy expected as a result of project
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) breadth of impact (population (# of businesses / jobs + sectors + time) | 1 - Minor Affects a small number of local businesses / jobs AND/OR a single, non-critical economic sector AND/OR Effects last less than 3 months | 2 - Some Affects some local businesses / jobs AND/OR a few, non-critical economic sectors AND/OR Effects last between 3 and 6 months | 3 - Moderate Affects a moderate number of local businesses / jobs AND/OR some non-critical economic sectors AND/OR Effects last between 6 and 12 months | 4 - Significant Affects a significant number of local businesses / jobs AND/OR many non-critical economic sectors and/or a single, critical economic sector AND/OR Effects last more than 1 year | 5 - Major Affects a majority of local businesses / jobs AND/OR multiple critical economic sectors AND/OR Effects are permanent
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
3.2.8 | GHG Reduction | Project results in increased or reduced GHG emissions | + / - GHG Emissions over 20 yr period | 1 - Significant Negative (--) Significant ongoing additional GHG emissions expected as a result of project | 2 - Negative Impact (-) Ongoing moderate additional GHG emissions or large, short-term additional GHG emissions expected as a result of project | 3 - Minor/No Impact No additional GHG emissions and no reduction in GHG emissions expected as a result of project | 4 - Positive Impact (+) Ongoing moderate reduction in GHG emissions or large, short-term reduction in GHG emissions expected as a result of project | 5 - Significant Positive (++) Ongoing significant reduction in GHG emissions expected as a result of project
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
3.3 Supplemental Criteria - Fill out all criteria
3.3.1 | Residual Risk | The risk to the related asset(s), operation(s) and/or service(s) associated with not completing the project in the medium term. | A) Consequence of not doing project in the next 3 to 5 years? | 1 - Insignificant or NA Small but noticeable impact on service. Minor inconvenience / potential for user complaint. Very little associated damage and/or remedial costs. | 2 - Minor Performance failure and/or decline in service. Small but noticeable impact on service. Minor inconvenience / potential for user complaint. Very little associated damage and/or remedial costs. | 3 - Moderate Performance failure and/or decline in service. Moderate impact on service. Significant, but short term inconvenience, likely to lead to user complaints. Potential for some limited associated damage and/or remedial costs. | 4 - Major Performance failure and/or decline in service. Serious impact on service. Significant extended inconvenience, likely to lead to strong user complaints. Potential for significant associated damage and/or remedial costs. | 5 -Severe Prolonged / persistent major failure and/or service deterioration. Major impact on service. Major ongoing inconvenience, likely to lead to strong, broad-based user complaints. Potential for major associated damage and/or very costly remedial measures.
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | B) Likelihood of impact of not doing project in the next 3 to 5 years? | 1 - Rare or NA May only occur in certain conditions Every 10+ years 0% to 10% | 2 - Unlikely Could occur some time Every 5 to 10 years 10% to 40% | 3 - Possible Might occur at some time Every 3 to 5 years 40% to 60% | 4 - Likely Will probably occur in most circumstances Every 2 to 3 years 60% to 90% | 5 -Almost Certain Almost certain to occur Annually or more frequently 90% to 100%
|  |  | Select from drop down list |  | Comments (Optional): Add comments here if you wish to justify the selection
|  |  | Selection Check: | Please Fill in All Sections (No Blanks)
Business Case - Capital Projects

## 4 - Suppl. Info (Optional)
Legend:
|  |  |  | FISCAL YR: | 2022 |  | Drop down list
|  |  |  | FUND: | General |  | Open text field
Version: v1 | [6 empty] | 0
4.0 SUPPLEMENTAL INFORMATION (OPTIONAL)
4.1 Additional Details (Optional)
4.1.1 Grant Funding - Details |  |  | NA | Refer to Tab 1, Section 1.2.3
| 4.1.1.a How much total funding is available? |  | 0 | Dollar Value (= NPC total, 2.1.1.b CAPEX - Expected External Funding for Project)
| 4.1.1.b How much (as a %) does the funding cover the Total Capital Cost? |  | 0% | Percentage (= 4.1.1.c Total Capital Cost Residual DIVIDED BY NPC total, 2.1.1.a CAPEX - Project Costs
| 4.1.1.c What is the Total Capital Cost Residual |  | 0 | Dollar Value (= NPC total, 2.1.1.a CAPEX - Project Costs LESS NPC total, 2.1.1.b CAPEX - Expected External Funding for Project)
| 4.1.1.d Are their any funding limitations or conditions |  | e.g. Describe the requirements that must be met to receive funding or scopes that will not be considered for funding |  |  |  | Text
| 4.1.1.e What is the alternative plan if you don't get funding |  | e.g. Describe alternate sources of funding, or whether project would be scoped down or not proceed if funding is not secured |  |  |  | Text
| 4.1.1.f What is the risk to external funding if the project does not proceed immediately? |  | 1 - Very Low Very limited funding available (< 10% of total project capital costs) from an identified source of external funding expected to be continuously available. | 2 - Low Limited funding available (10% to < 50% of total project capital costs) from an identified source of external funding expected to be continuously available. | 3 - Moderate Funding available (50% to 100% of total project capital costs) from an identified source of external funding expected to be available next year. | 4 - High Project must proceed immediately to leverage limited identified funds (< 50% of total project capital costs) | 5 - Very High Project must proceed immediately to leverage significant identified funds (50% to 100% of total project capital costs)
|  |  | NA | Select from drop-down list
4.1.2 Project Interdependencies - Details |  |  | NA | Refer to Tab 1, Section 1.2.4
| (i.e. impacts, positively or negatively, other department's operations, other assets, or other services, or presents opportunities for collaboration, corridor optimization, or similar) * NON-RESOURCING-RELATED IMPACTS |  | Fill out up to 3 interdependencies below
| 4.1.2.a.i Interdependency 1 |  | Department | Asset (if applicable) | Impact on operations / assets / services
[5 empty] | NA | Select from drop-down list
| 4.1.2.a.ii Interdependency 1 - Description |  | Describe the interdependency
| 4.1.2.a.iii Interdependency 1 - Level of Opportunity/Impact |  | 1 - Very Low | 2 - Low | 3 - Moderate | 4 - High | 5 - Very High
|  |  | NA | Select from drop-down list
| 4.1.2.b.i Interdependency 2 |  | Department | Asset (if appl.) | Impact on operations / assets / services
[5 empty] | NA | Select from drop-down list
| 4.1.2.b.ii Interdependency 2 - Description |  | Describe the interdependency
| 4.1.2.b.iii Interdependency 2 - Level of Opportunity/Impact |  | 1 - Very Low | 2 - Low | 3 - Moderate | 4 - High | 5 - Very High
|  |  | NA | Select from drop-down list
| 4.1.2.c.i Interdependency 3 |  | Department | Asset (if appl.) | Impact on operations / assets / services
[5 empty] | NA | Select from drop-down list
| 4.1.2.c.ii Interdependency 3 - Description |  | Describe the interdependency
| 4.1.2.c.iii Interdependency 3 - Level of Opportunity/Impact |  | 1 - Very Low | 2 - Low | 3 - Moderate | 4 - High | 5 - Very High
|  |  | NA | Select from drop-down list
4.1.3 Support of Strategic Initiative - Details |  |  | NA | Refer to Tab 1, Section 1.2.5
| 4.1.3.a Describe the source of the strategic initiative (i.e. the strategic priority it is fulfilling) and the project's strategic importance or alignment to a current strategic priority |  | e.g. Resiliency, DT vibrancy, infrastructure investment |  |  |  | Text
| 4.1.3.b Level of Strategic Importance / Alignment |  | 1 - Very Low Project has very low organizational strategic importance. OR Makes no contribution to a current strategic priority. | 2 - Low Project has low organizational strategic importance. OR Makes a minor contribution to a current strategic priority. | 3 - Moderate Project has moderate organizational strategic importance. OR Makes a moderate contribution to current strategic priority(s). | 4 - High Project has high organizational strategic importance. OR Makes a significant contribution to current strategic priority(s). | 5 - Very High Project has very high organizational strategic importance. OR Fully achieves current strategic priority(s).
|  |  | NA | Select from drop-down list
4.1.4 Is the project replacing an existing asset? |  |  | NA | Refer to Tab 1, Section 1.2.6
4.1.4.a How is the existing asset being disposed of?
|  |  | 1 - No Recycling or Repurposing Asset will be fully disposed of with no materials recycled or repurposed | 2 - Some Recycling or Repurposing Some materials will be recycled or repurposed during disposal | 3 - Moderate Recycling or Repurposing Approximately half of materials will be recycled or repurposed during disposal | 4 - Significant Recycling or Repurposing Most materials will be recycled or repurposed during disposal | 5 - Full Recycling or Repurposing All materials will be recycled or repurposed during disposal
|  |  | NA | Select from drop-down list
4.1.4.b Did you consider utilizing the services of natural assets in your project planning?
|  |  | No | Select from drop-down list
|  | 4.1.4.b.i Explain why you did or did not consider the services of natural assets | Explain why or why not
| 4.1.4.c Does the project affect the carbon dependency of the greater District infrastructure system? (Compared to the existing condition) |  | 1 - Greatly Increases District Carbon Dependency Embedded carbon footprint of the replacement asset is very large when compared to other options. Creates a requirement for other carbon intensive assets in future. Greatly increases the amount of fossil fuels used by the District. 'Locks in' fossil fuel use for a very long time, with no options for mitigating this usage in future. Makes GHG mitigation efforts much more difficult. | 2 - Somewhat Increases District Carbon Dependency Embedded carbon footprint of the replacement asset is large when compared to other options. Creates a bias towards other carbon intensive assets in future. Increases the amount of fossil fuels used by the District. 'Locks in' fossil fuel use for a long time, with limited options for mitigating this usage in future. Makes GHG mitigation efforts more difficult. | 3 - Does Not Change District Carbon Dependency Embedded carbon footprint of the replacement asset is similar to other options. Does not create a requirement for or bias towards other carbon intensive assets in future. The amount of fossil fuels used by the District remains the same. Does not 'Lock in' fossil fuel use. Does not affect options for mitigating fossil fuel usage in future. Does not affect GHG mitigation efforts. | 4 - Somewhat Reduces District Carbon Dependency Embedded carbon footprint of the replacement asset is lower than other options. Creates a bias towards other low carbon assets in future. Reduces the amount of fossil fuels used by the District. Allows for decreasing fossil fuel use in future. Enhances GHG mitigation efforts. | 5 - Greatly Reduces District Carbon Dependency Utilizes a carbon-neutral or carbon-negative replacement asset. Creates a requirement for other low carbon assets in future. Substantially reduces the amount of fossil fuels used by the District. Allows for substantial additional reductions of fossil fuel use in future. Greatly enhances GHG mitigation efforts.
|  |  | 3 | Select from drop-down list
| 4.1.4.d AFTER the asset is replaced, what will be the level of resiliency of the asset/system and/or service/maintenance/operations? |  | 1 - Asset / System Not Resilient Asset / system is not able to mitigate or manage disaster events. Service recovery times are much longer than expected. There is no redundancy, coverage, backup, or hardening for critical assets or systems. It is very difficult to identify asset failure, asset system performance degredation, and/or service degredation. | 2 - Asset / System Minimally Resilient Asset / system is not able to mitigate or manage expected disaster events at current intesities and frequencies. Service recovery times are longer than expected. There is some redundancy, coverage, backup, or hardening for some critical assets or systems. It is difficult to identify asset failure, asset system performance degredation, and/or service degredation. | 3 - Asset / System Somewhat Resilient Asset / system is able to mitigate or manage expected disaster events at current intesities and frequencies. Service recovery times are long, but within expectations. There is redundancy, coverage, backup, or hardening for many critical assets or systems. Asset failure, asset system performance degredation, and/or service degredation can normally be identified with time. | 4 - Asset / System Moderately Resilient Asset / system is able to mitigate or manage expected disaster events at future projected intesities and frequencies under low consequence climate change scenarios. Service recovery times are currently within expectations. There is redundancy, coverage, backup, or hardening for all critical assets or systems. Asset failure, asset system performance degredation, and/or service degredation is almost always identified in a timely manner. | 5 - Asset / System Highly Resilient Asset / system is able to mitigate and manage expected disaster events under high consequence climate change scenarios (severe intesities at high frequencies). Service recovery times will continue to be within expectations in future. There is sufficient redundancy, coverage, backup, and hardening for all necessary assets and systems. Asset failure, asset system performance degredation, and service degredation are automatically identified quickly.
|  |  | NA | Select from drop-down list
4.1.5 Does the project have ecological impacts? |  |  | NA | Refer to Tab 1, Section 1.2.7
| 4.1.5.a Does the project affect the ecological integrity of the area (e.g. habitat, wildlife, vegetation, canopy cover, air quality, etc.)? |  | Impact?
|  |  | NA | Select from drop-down list
|  | 4.1.5.a.i Impacts to Ecological Integrity - Description | Describe the impact(s)
|  | 4.1.5.a.ii Impacts to Ecological Integrity - Level of Impact | 1 - Overall Significant Negative Impact(s) | 2 - Overall Negative Impact(s) | 3 - No Impacts OR Balanced Impacts | 4 - Overall Positive Impact(s) | 5 - Overall Significant Positive Impact(s)
|  |  | 3 | Select from drop-down list
| 4.1.5.b Does the project impact bodies of water, streams, wetlands, riparian areas, or other aspects of the watershed? |  | Impact?
|  |  | NA | Select from drop-down list
|  | 4.1.5.b.i Impact to Water - Description | Describe the impact(s)
|  | 4.1.5.b.ii Impact to Water - Level of Impact | 1 - Overall Significant Negative Impact(s) | 2 - Overall Negative Impact(s) | 3 - No Impacts OR Balanced Impacts | 4 - Overall Positive Impact(s) | 5 - Overall Significant Positive Impact(s)
|  |  | 3 | Select from drop-down list
| 4.1.5.c Does the project impact soil quality (degredation, admixing, compaction), erosion/erosion risk, ground stability, etc.? |  | Impact?
|  |  | NA | Select from drop-down list
|  | 4.1.5.d.i Impact to Soil - Description | Describe the impact(s)
|  | 4.1.5.d.ii Impact to Soil - Level of Impact | 1 - Overall Significant Negative Impact(s) | 2 - Overall Negative Impact(s) | 3 - No Impacts OR Balanced Impacts | 4 - Overall Positive Impact(s) | 5 - Overall Significant Positive Impact(s)
|  |  | 3 | Select from drop-down list
4.2 Other Considerations (Optional)
4.2.1 Community sensitivity to service
(e.g.: Affects visible or top-of-mind issue in community, or community has controversial or negative views towards service or project, whether broad-based or narrowly effecting a group, interest or demographic)
| 4.2.1.a Community sensitivity level? |  | 1 - Very Low | 2 - Low | 3 - Moderate | 4 - High | 5 - Very High
|  |  | NA | Select from drop-down list
| 4.2.1.b Explain the sensitivity of the project and/or service to the community and the relevant group/interest/demographic effected | [5 empty] | Text
4.2.2 Project Uncertainties
(including reliability of assumptions/data on needs, benefits, outcomes, risks, affects of project on asset system, environmental impacts, social impacts, economic impacts, timescale effects, etc.)
| 4.2.2.a Overall uncertainty level of project |  | 1 - Very Low | 2 - Low | 3 - Moderate | 4 - High | 5 - Very High
|  |  | NA | Select from drop-down list
| 4.2.2.b Explain the key uncertainties associated with the project and their potential impacts | [5 empty] | Text
4.3 Needs Identification (Optional - M, L, XL Only)
4.3.1 Life-Cycle Stage |  |  |  |  | Select from drop down list
4.3.2 Current / Future State Gap |  |  | Describe the current state of the asset or the service being impacted, the result or outcome to be attained after the project is completed, and the difference between those two states. |  |  |  | Text
4.3.3 Root Cause Description |  |  | Describe the underlying reasons (root causes) why the service and/or asset were impacted. |  |  |  | Text
4.3.4 Identify External Stakeholder Interests & Implications |  |  | Identify and describe any external sources of demand for the project (e.g. complaints, requests, petitions, council presentations, etc.) and how this has affected the development of the business case and could affect the project moving forward. |  |  |  | Text
4.3.5 Identify Other Relevent Contextual Information |  |  | Identify and describe any other important information that has informed the idenfication of the need for the project. |  |  |  | Text
4.4 Data & Evidence (Optional - M, L, XL Only)
4.4.1 Identify supplemental info or data used to develop the business case | [6 empty] | Text
4.4.2 Identify key internal info or data required for the project | [6 empty] | Text
4.4.3 Identify key external info or data required for the project | [6 empty] | Text
4.4.4 Explain any data quality issues to be addressed for the project | [6 empty] | Text
4.4.5 Explain any data gaps to be addressed or primary data collection required for the project | [6 empty] | Text
4.5 Supplemental Analyses (Optional - L & XL ONLY)
4.5.1 Are there supplemental analyses for the project?
| Select 'Yes' if there are supplemental analyses that justify the need for the project, support the information in this business case, or provide additional details about the project or the options assessed. Options include: Contextual analyses, benefit/cost analyses, comprehensive financial analysis, risk analyses, evironmental impact assessments, socio-economic impact assessments, or similar Fill in the applicable information below to direct decision-makers to this information. Space has been provided for up to 5 analyses. |  | No | Select from drop down list
4.5.2 Supplemental Analysis #1
| 4.5.1.a Name of analysis |  | Name of report or analysis |  |  |  | Text
| 4.5.1.b Short description of analysis |  | Short description of report or analysis and its relevance to the project |  |  |  | Text
| 4.5.1.b File location of analysis |  | Link to District file location of report or analysis |  |  |  | Text
4.5.3 Supplemental Analysis #2
| 4.5.1.a Name of analysis |  | Name of report or analysis |  |  |  | Text
| 4.5.1.b Short description of analysis |  | Short description of report or analysis and its relevance to the project |  |  |  | Text
| 4.5.1.b File location of analysis |  | Link to District file location of report or analysis |  |  |  | Text
4.5.4 Supplemental Analysis #3
| 4.5.1.a Name of analysis |  | Name of report or analysis |  |  |  | Text
| 4.5.1.b Short description of analysis |  | Short description of report or analysis and its relevance to the project |  |  |  | Text
| 4.5.1.b File location of analysis |  | Link to District file location of report or analysis |  |  |  | Text
4.5.5 Supplemental Analysis #4
| 4.5.1.a Name of analysis |  | Name of report or analysis |  |  |  | Text
| 4.5.1.b Short description of analysis |  | Short description of report or analysis and its relevance to the project |  |  |  | Text
| 4.5.1.b File location of analysis |  | Link to District file location of report or analysis |  |  |  | Text
4.5.6 Supplemental Analysis #5
| 4.5.1.a Name of analysis |  | Name of report or analysis |  |  |  | Text
| 4.5.1.b Short description of analysis |  | Short description of report or analysis and its relevance to the project |  |  |  | Text
| 4.5.1.b File location of analysis |  | Link to District file location of report or analysis |  |  |  | Text
Business Case - Capital Projects

## 5 - Options Analysis (Optional)
Legend:
[7 empty] | FISCAL YR: | 2022 | [5 empty] | Drop down list
[7 empty] | FUND: | General | [5 empty] | Open text field
Version: v1 | [14 empty] | 0
5.0 OPTIONS ANALYSIS (OPTIONAL)
5.1 Preferred Option (Optional - L, XL Projects ONLY)
5.1.1 Preferred Option for Project | [5 empty] | Select from drop down list
5.2 Option 1 Analysis (Optional - L, XL Projects ONLY)
5.2.1 Option 1 - Option Description
| (describe the option and how it differs from 1.1.2 Short Project Description) | [10 empty] | Text
5.2.2 Option 1 - Life-Cycle Financial Impact
Fill out only those that apply
| * | Sec. # | Description |  |  | Net Present Cost** | YR 1 | YR 2 | YR 3 | YR 4 | YR 5 | YR 6 | YR 7 | YR 8 | YR 9 | YR 10 | YR 11 | YR 12 | YR 13 | YR 14 | YR 15 | YR 16 | YR 17 | YR 18 | YR 19 | YR 20
|  |  | (estimate the difference from before project to after project) |  |  | ("NPC") | bar: YR 1 to YR 20
| + | 5.2.2.a | CAPEX - Project Costs (purchase/engineering/construction costs, incl. resourcing) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - | 5.2.2.b | CAPEX - Expected External Funding for Project |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.2.2.c | CAPEX - Change in Major Maintenance / Life-Cycle Activities Costs*** |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.2.2.d | OPEX - New Revenues From Project / Reduction of Service Revenues |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.2.2.e | OPEX - Change in Regular Operating and Maintenance Costs**** |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL FINANCIAL COST (RETURN) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| * | Increase in costs OR decrease in revenues = Positive $ amount (+) Decrease in costs (i.e. cost savings) OR increase in revenues = Negative $ amount (-)
| ** | Assumes Yr 1 is current year
| *** | Change in costs to conduct major maintenance, or to refurbish, replace or upgrade the asset related to the project, including renewal or major maintenance periods. These are maintenance projects >$10,000 which should be noted as CAPEX not OPEX. If this project is for a new asset, the future lifecycle costs associated with this asset will be entered into this row as a (+) value. If this project involves an existing asset, future lifecycle costs will be entered as a (+) value in the year they are expected to occur if the project is completed. Future lifecycle costs will be entered as a (-) value in the year they would have been incurred if the project is not completed. See training notes for further explanation.
| **** | Including change in risk costs (cost of reasonably expected major adverse event @ expected frequency of occurance) and other avoided costs (fines, penalties, fees, or any other one-off costs not already captured)
5.2.2.f Additional Information on Lifecycle Financial Impacts |  |  |  | Add Comments |  |  | YR 5: Text
Use this section to provide justification for inputs in the financial impacts table. This may include an explanation of change in major maintanance activities, assumptions made in the change in revenues or change in OPEX, links to supporting documentation, or any other comments relavent to others who will review the project. | bar: YR 1 to YR 4
5.2.3 Option 1 - Asset Refurbishment / Renewal Information
| 5.2.3.a New or Existing Asset? |  |  | Does this project create a new asset where there was not one before, or does this project involve the refurbishment/ replacement of an already existing asset?
|  |  |  | Existing Asset |  | Select from drop down list
| 5.2.3.b Estimated useful life of Related Asset (if applicable) |  |  | If applicable, estimate the expected design life the related asset (i.e. how often will it need to be renewed)
|  |  |  | 0 | Period (in Years)
| 5.2.3.c Estimated Remaining Useful Life of Related Asset (if applicable) |  |  | If applicable, estimate the remaining useful life of the related asset (must be less than 5.2.3.a)
|  |  |  | 0 | (in Years)
5.2.4 Option 1 - Level of Impact to Internal Resources
| (it is assumed that all external staff and equipment needs are included in the project life cycle financial impacts only) |  |  | 1 - Insignificant Minimal short term staff and/or equipment hours required to resource project; No additional ongoing staff and/or equipment hours required as a result of the project |  | 2 - Minor Some short term staff and/or equipment hours required to resource project (covered by capital projects staffing reserves); Minimal additional ongoing staff and/or equipment hours required as a result of the project | YR 1: 3 - Moderate Significant short term staff and/or equipment hours required to resource project (NOT covered by capital projects staffing reserves); Minimal additional ongoing staff and/or equipment hours required as a result of the project; YR 3: 4 - Major New short term staff position required and/or significant equipment hours required to resource project (NOT covered by capital projects staffing reserves); Some additional ongoing staff and/or equipment hours required as a result of the project; YR 5: 5 - Severe New staff position and/or new equipment needed to resource continuing O&M as a result of the project
|  |  |  | NA | Select from drop down list
5.2.5 Option 1 - Internal Resourcing Impacts Description
| 5.2.5.a Describe internal staff requirements for design/construction phase, including estimated hours needed by position | [5 empty] | YR 6: Text
| 5.2.5.b Describe internal equipment/fleet requirements for design/construction phase, including estimated hours needed by equipment type | [5 empty] | YR 6: Text
| 5.2.5.c Describe internal staffing impacts for ongoing operations and maintenance, including estimated FTEs required by position | [5 empty] | YR 6: Text
| 5.2.5.d Describe internal equipment/fleet impacts for ongoing operations and maintenance, including new equipment needed | [5 empty] | YR 6: Text
5.3 Option 2 Analysis (Optional - L, XL Projects ONLY)
5.3.1 Option 2 - Option Description
| (describe the option and how it differs from 1.1.2 Short Project Description) | [5 empty] | YR 6: Text
5.3.2 Option 2 - Life-Cycle Financial Impact
Fill out only those that apply
| * | Sec. # | Description |  |  | Net Present Cost** | YR 1 | YR 2 | YR 3 | YR 4 | YR 5 | YR 6 | YR 7 | YR 8 | YR 9 | YR 10 | YR 11 | YR 12 | YR 13 | YR 14 | YR 15 | YR 16 | YR 17 | YR 18 | YR 19 | YR 20
|  |  | (estimate the difference from before project to after project) |  |  | ("NPC") | bar: YR 1 to YR 20
| + | 5.3.2.a | CAPEX - Project Costs (purchase/engineering/construction costs, incl. resourcing) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - | 5.3.2.b | CAPEX - Expected External Funding for Project |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.3.2.c | CAPEX - Change in Major Maintenance / Life-Cycle Activities Costs*** |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.3.2.d | OPEX - New Revenues From Project / Reduction of Service Revenues |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.3.2.e | OPEX - Change in Regular Operating and Maintenance Costs**** |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL FINANCIAL COST (RETURN) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| * | Increase in costs OR decrease in revenues = Positive $ amount (+) Decrease in costs (i.e. cost savings) OR increase in revenues = Negative $ amount (-)
| ** | Assumes Yr 1 is current year
| *** | Change in costs to conduct major maintenance, or to refurbish, replace or upgrade the asset related to the project, including renewal or major maintenance periods. These are maintenance projects >$10,000 which should be noted as CAPEX not OPEX. If this project is for a new asset, the future lifecycle costs associated with this asset will be entered into this row as a (+) value. If this project involves an existing asset, future lifecycle costs will be entered as a (+) value in the year they are expected to occur if the project is completed. Future lifecycle costs will be entered as a (-) value in the year they would have been incurred if the project is not completed. See training notes for further explanation.
| **** | Including change in risk costs (cost of reasonably expected major adverse event @ expected frequency of occurance) and other avoided costs (fines, penalties, fees, or any other one-off costs not already captured)
5.3.2.f Additional Information on Lifecycle Financial Impacts |  |  |  | Add Comments |  |  | YR 5: Text
Use this section to provide justification for inputs in the financial impacts table. This may include an explanation of change in major maintanance activities, assumptions made in the change in revenues or change in OPEX, links to supporting documentation, or any other comments relavent to others who will review the project. | bar: YR 1 to YR 4
5.3.3 Option 2 - Asset Refurbishment / Renewal Information
| 5.3.3.a New or Existing Asset? |  |  | Does this project create a new asset where there was not one before, or does this project involve the refurbishment/ replacement of an already existing asset?
|  |  |  | Existing Asset |  | Select from drop down list
| 5.3.3.b Expected Useful life of related asset |  |  | If applicable, estimate the expected design life the related asset (i.e. how often will it need to be renewed)
|  |  |  | 0 | Period (in Years)
| 5.3.3.c Estimated Remaining Useful Life of Related Asset (if applicable) |  |  | If applicable, estimate the remaining useful life of the related asset (must be less than 5.3.3.a)
|  |  |  | 0 | (in Years)
5.3.4 Option 2 - Level of Impact to Internal Resources
| (it is assumed that all external staff and equipment needs are included in the project life cycle financial impacts only) |  |  | 1 - Insignificant Minimal short term staff and/or equipment hours required to resource project; No additional ongoing staff and/or equipment hours required as a result of the project |  | 2 - Minor Some short term staff and/or equipment hours required to resource project (covered by capital projects staffing reserves); Minimal additional ongoing staff and/or equipment hours required as a result of the project | YR 1: 3 - Moderate Significant short term staff and/or equipment hours required to resource project (NOT covered by capital projects staffing reserves); Minimal additional ongoing staff and/or equipment hours required as a result of the project; YR 3: 4 - Major New short term staff position required and/or significant equipment hours required to resource project (NOT covered by capital projects staffing reserves); Some additional ongoing staff and/or equipment hours required as a result of the project; YR 5: 5 - Severe New staff position and/or new equipment needed to resource continuing O&M as a result of the project
|  |  |  | NA | Select from drop down list
5.3.5 Option 2 - Internal Resourcing Impacts Description
| 5.3.5.a Describe internal staff requirements for design/construction phase, including estimated hours needed by position | [5 empty] | YR 6: Text
| 5.3.5.b Describe internal equipment/fleet requirements for design/construction phase, including estimated hours needed by equipment type | [5 empty] | YR 6: Text
| 5.3.5.c Describe internal staffing impacts for ongoing operations and maintenance, including estimated FTEs required by position | [5 empty] | YR 6: Text
| 5.3.5.d Describe internal equipment/fleet impacts for ongoing operations and maintenance, including new equipment needed | [5 empty] | YR 6: Text
5.4 Option 3 Analysis (Optional - L, XL Projects ONLY)
5.4.1 Option 3 - Option Description
| (describe the option and how it differs from 1.1.2 Short Project Description) | [5 empty] | YR 6: Text
5.4.2 Option 3 - Life-Cycle Financial Impact
Fill out only those that apply
| * | Sec. # | Description |  |  | Net Present Cost** | YR 1 | YR 2 | YR 3 | YR 4 | YR 5 | YR 6 | YR 7 | YR 8 | YR 9 | YR 10 | YR 11 | YR 12 | YR 13 | YR 14 | YR 15 | YR 16 | YR 17 | YR 18 | YR 19 | YR 20
|  |  | (estimate the difference from before project to after project) |  |  | ("NPC") | bar: YR 1 to YR 20
| + | 5.4.2.a | CAPEX - Project Costs (purchase/engineering/construction costs, incl. resourcing) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - | 5.4.2.b | CAPEX - Expected External Funding for Project |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.4.2.c | CAPEX - Change in Major Maintenance / Life-Cycle Activities Costs*** |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.4.2.d | OPEX - New Revenues From Project / Reduction of Service Revenues |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| + / - | 5.4.2.e | OPEX - Change in Regular Operating and Maintenance Costs**** |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL FINANCIAL COST (RETURN) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| * | Increase in costs OR decrease in revenues = Positive $ amount (+) Decrease in costs (i.e. cost savings) OR increase in revenues = Negative $ amount (-)
| ** | Assumes Yr 1 is current year
| *** | Change in costs to conduct major maintenance, or to refurbish, replace or upgrade the asset related to the project, including renewal or major maintenance periods. These are maintenance projects >$10,000 which should be noted as CAPEX not OPEX. If this project is for a new asset, the future lifecycle costs associated with this asset will be entered into this row as a (+) value. If this project involves an existing asset, future lifecycle costs will be entered as a (+) value in the year they are expected to occur if the project is completed. Future lifecycle costs will be entered as a (-) value in the year they would have been incurred if the project is not completed. See training notes for further explanation.
| **** | Including change in risk costs (cost of reasonably expected major adverse event @ expected frequency of occurance) and other avoided costs (fines, penalties, fees, or any other one-off costs not already captured)
5.4.2.f Additional Information on Lifecycle Financial Impacts |  |  |  | Add Comments |  |  | YR 5: Text
Use this section to provide justification for inputs in the financial impacts table. This may include an explanation of change in major maintanance activities, assumptions made in the change in revenues or change in OPEX, links to supporting documentation, or any other comments relavent to others who will review the project. | bar: YR 1 to YR 4
5.4.3 Option 3 - Asset Refurbishment / Renewal Information
| 5.4.3.a New or Existing Asset? |  |  | Does this project create a new asset where there was not one before, or does this project involve the refurbishment/ replacement of an already existing asset?
|  |  |  | Existing Asset |  | Select from drop down list
| 5.4.3.b Expected Usefule life of Related Asset (if applicable) |  |  | If applicable, estimate the expected design life the related asset (i.e. how often will it need to be renewed)
|  |  |  | 0 | Period (in Years)
| 5.4.3.c Estimated Remaining Useful Life of Related Asset (if applicable) |  |  | If applicable, estimate the remaining useful life of the related asset (must be less than 5.4.3.a)
|  |  |  | 0 | (in Years)
5.4.4 Option 3 - Level of Impact to Internal Resources
| (it is assumed that all external staff and equipment needs are included in the project life cycle financial impacts only) |  |  | 1 - Insignificant Minimal short term staff and/or equipment hours required to resource project; No additional ongoing staff and/or equipment hours required as a result of the project |  | 2 - Minor Some short term staff and/or equipment hours required to resource project (covered by capital projects staffing reserves); Minimal additional ongoing staff and/or equipment hours required as a result of the project | YR 1: 3 - Moderate Significant short term staff and/or equipment hours required to resource project (NOT covered by capital projects staffing reserves); Minimal additional ongoing staff and/or equipment hours required as a result of the project; YR 3: 4 - Major New short term staff position required and/or significant equipment hours required to resource project (NOT covered by capital projects staffing reserves); Some additional ongoing staff and/or equipment hours required as a result of the project; YR 5: 5 - Severe New staff position and/or new equipment needed to resource continuing O&M as a result of the project
|  |  |  | NA | Select from drop down list
5.4.5 Option 3 - Internal Resourcing Impacts Description
| 5.4.5.a Describe internal staff requirements for design/construction phase, including estimated hours needed by position | [5 empty] | YR 6: Text
| 5.4.5.b Describe internal equipment/fleet requirements for design/construction phase, including estimated hours needed by equipment type | [5 empty] | YR 6: Text
| 5.4.5.c Describe internal staffing impacts for ongoing operations and maintenance, including estimated FTEs required by position | [5 empty] | YR 6: Text
| 5.4.5.d Describe internal equipment/fleet impacts for ongoing operations and maintenance, including new equipment needed | [5 empty] | YR 6: Text
Business Case - Capital Projects

## (Output) (hidden)
Model Output
| Field | Field Code | Entry | Field Type | Field Options/Constraints | Default | Notes
| FiscalYear | FiscalYr | 2022 | # | whole number, btw 2020 and 2100 (cannot be blank) | 2020 | will require update to current year going forward
| Fund | Fund | GRL | Drop-Down List | see "(admin)" tab - column C (cannot be blank) | [Fund of template]
| Discount Rate | DiscRate | 5% | % | N/A | 5% | Finance to confirm
| File Name | FileNam | 2021-Water_BusCase_Template | Text | N/A | [Excel File Name]
Project Description
| 1.1.1 Project File Name | ProjFileNam | unique_proj_name | Text | Open, project numbers should be unique | descriptive text
| 1.1.2 Project Name | ProjNam | Name of project - Should be reasonably short and descriptive | Text | Open | descriptive text
| 1.1.3.a Purpose of the Project | ProjPurp | Briefly describe the main problem that the project is intended to solve. | Text | Open | Briefly describe the main problem that the project is intended to solve.
| 1.1.3b Project Description | ProjDesc | Describe the work to be completed in no more than three sentences | Text | Open | Describe the work to be completed in no more than three sentences
| 1.1.4 Department (for General Fund only) | ProjDept | N/A | Drop-Down List | see "(admin)" tab - column B (cannot be blank) | N/A
| 1.1.5 Project Contact | Contact | Name of primary contact for project information | Text | Open | Name of primary contact for project information
| 1.1.6 Project Location(s) | ProjLoc | Street number and name or other relevant map reference. For linear projects identify starting and ending locations. For projects with multiple locations specify 'multiple' and provide link to supporting documentation | Text | Open | Street number and name or other relevant map reference. For linear projects identify starting and ending locations. For projects with multiple locations specify "multiple" and provide link to supporting documentation
| 1.1.7.a Planned Start Date | ProjStrtDate | 2021-01-01 | Date (MM/YYYY) | > 1/1/2019 | 2020-01-01 | will require update to current year going forward
| 1.1.8 Project Duration | ProjDur | 0 | # of Months | whole number, btw 0 and 60 (cannot be blank) | 0
| 1.1.9 Project Size | ProjSize | 0 | Drop-Down List | S, M, L, XL (cannot be blank) | blank
| 1.2.1 Project Rationale | ProjRat | 0 | Drop-Down List | see "(admin)" tab - column D (cannot be blank) | blank
| 1.2.2 Sustainability Co-Benefits (Select all that apply) | SustainCoBen
| 1.2.3 Can the Project be Grant Funded? | GrntFund | Unknown | Drop-Down List | Yes/No/Unknown | Unknown
| 1.2.4 Are There Project Interdependencies? | ProjInterdep | Unknown | Drop-Down List | Yes/No/Unknown | Unknown
| 1.2.5 Does the Project Support a Current Strategic Initiative? | StratInit | Unknown | Drop-Down List | Yes/No/Unknown | Unknown
| 1.2.6 Is the Project Replacing an Existing Asset? | AssetReplace | Unknown | Drop-Down List | Yes/No/Unknown | Unknown
| 1.2.7 Does the Project have Ecological Impacts? | EcologicImp | Unknown | Drop-Down List | Yes/No/Unknown | Unknown
Project Status
| 1.3.2.a Project Status | StatProj | Project Description Incomplete | Text | Project Description Incomplete, Project Description Complete, Gate 1 Approved, Business Case Complete, Gate 2 Approved, Ready for Prioritization, Ready for Model Archived | Project Description Incomplete | formula not editable
| 1.3.2.b Project Description Complete? | StatDescCmpl | No | Drop-Down List | Yes / No | No
| 1.3.2.c Project Description (GATE 1) Approval | StatGate1Aprv | No | Drop-Down List | Yes / No | No
| 1.3.2.d Business Case Complete? | StatBCCmpl | No | Drop-Down List | Yes / No | No
| 1.3.2.e Business Case (GATE 2) Approval | StatGate2Aprv | No | Drop-Down List | Yes / No | No
| 1.3.2.f Criteria Selections Review (GATE 3) Approval? | StatPrReady | No | Drop-Down List | Yes / No | No
| #REF! | StatGate3Aprv | No | Drop-Down List | Yes / No | No
| 1.3.3 Business Case Status | StatBusCase | Active | Drop-Down List | Active / Archived / Budgeted | Active
Project Financial Information
| CAPEX - Project Costs - NPC | FnCPXPCNPC | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Project Costs - Yr 1 | FnCPXPCYr1 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Project Costs - Yr 2 | FnCPXPCYr2 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Project Costs - Yr 3 | FnCPXPCYr3 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Project Costs - Yr 4 | FnCPXPCYr4 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Project Costs - Yr 5 | FnCPXPCYr5 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Expected External Funding - NPC | FnCPXEFNPC | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Expected External Funding - Yr 1 | FnCPXEF1 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Expected External Funding - Yr 2 | FnCPXEF2 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Expected External Funding - Yr 3 | FnCPXEF3 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Expected External Funding - Yr 4 | FnCPXEF4 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Expected External Funding - Yr 5 | FnCPXEF5 | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| CAPEX - Change in Major Maint / Life-Cycle Costs - NPC | FnCPXMLNPC | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| OPEX - Change in Revenues - NPC | FnOPXRCNPC | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| OPEX - Change in Regular O&M Costs - NPC | FnOPXOMNPC | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| TOTAL FINANCIAL COST (RETURN) - NPC | FnTLCNPC | 0 | $ | positive (cost) or negative (revenue/cost saving) | 0
| 2.1.2.a Is this a new asset? | NewAsset? | 0 | Drop-Down List | Existing Asset/New Asset | Existing Asset
| 2.1.2.b Expected Useful Life of Related Asset (if applicable) | UsefulLife | 0 | # | # | 0
| 2.1.2.c Estimated Remaining Useful Life of Related Asset (if applicable) | UsefulLifeRem | 0 | # | # < 2.1.2.b | 0
| 2.2.1 Level of Impact to Internal Resources | LOIIntRes | 0 | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA
Decision Criteria
| 3.1.1 Improve or Increase LOS (A) Level of Impact | CrIncLOSLOI | NA | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA | NA = 0
| 3.1.1 Improve or Increase LOS (B) Breadth of Impact | CrIncLOSBOI | NA | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA | NA = 0
| 3.1.2 Maintain/Restore LOS - Same Capacity (A) Consequence | CrMtnLOSSCCon | NA | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA | NA = 0
| 3.1.2 Maintain/Restore LOS - Same Capacity (B) Likelihood | CrMtnLOSSCLik | NA | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA | NA = 0
| 3.1.2 Maintain/Restore LOS - Same Capacity (C) Criticality | CrMtnLOSSCCrit | NA | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA | NA = 0
| 3.1.3 Maintain/Restore LOS - Increase Capacity (A) Level of Need | CrMtnLOSICLON | NA | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA | NA = 0
| 3.1.3 Maintain/Restore LOS - Increase Capacity (B) Criticality | CrMtnLOSICCrit | NA | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA | NA = 0
| 3.2.1 Compliance (A) Consequence | CrCompCon | 0 | Drop-Down List | NA, 1, 2, 3, 4, 5 | blank | NA = 0
| 3.2.1 Compliance (B) Likelihood | CrCompLik | 0 | Drop-Down List | NA, 1, 2, 3, 4, 5 | blank | NA = 0
| 3.2.2 Health & Safety Impact (A) Consequence | CrHSICons | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | 1 = 0
| 3.2.2 Health & Safety Impact (B) Likelihood | CrHSILik | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | 1 = 0
| 3.2.2 Health & Safety Impact (C) Scale | CrHSISca | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | 3 = neutral
| 3.2.3 Resiliency | CrRslcy | 0 | Drop-Down List | NA, 1, 2, 3, 4, 5 | blank | NA = 0
| 3.2.4 Life Cycle Financial Impact | CrLCFI | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | negative (1,2) - neutral (3) - positive (4,5); neutral (3) = 0
| 3.2.5 Community Benefit - Environmental (A) Level of Impact | CrCBEnvLOI | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | negative (1,2) - neutral (3) - positive (4,5); neutral (3) = 0
| 3.2.5 Community Benefit - Environmental (B) Breadth of Impact | CrCBEnvBOI | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | If Impact = (3) (no impact), Breadth has no effect on score
| 3.2.6 Community Benefit - Social / Cultural (A) Level of Impact | CrCBSocLOI | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | negative (1,2) - neutral (3) - positive (4,5); neutral (3) = 0
| 3.2.6 Community Benefit - Social / Cultural (B) Breadth of Impact | CrCBSocBOI | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | If Impact = (3) (no impact), Breadth has no effect on score
| 3.2.7 Community Benefit - Economic (A) Level of Impact | CrCBEconLOI | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | negative (1,2) - neutral (3) - positive (4,5); neutral (3) = 0
| 3.2.7 Community Benefit - Economic (B) Breadth of Impact | CrCBEconBOI | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | If Impact = (3) (no impact), Breadth has no effect on score
| 3.2.8 GHG Reduction | CrGHGReduc | 0 | Drop-Down List | 1, 2, 3, 4, 5 | blank | negative (1,2) - neutral (3) - positive (4,5); neutral (3) = 0
Supplemental Criteria
| 2.2.1 Level of Impact to Internal Resources | SCrIntResLOI | 0 | Drop-Down List | NA, 1, 2, 3, 4, 5 | NA | NA = 0
| 3.3.1 Residual Risk (A) Consequence | ScrResRiskCon | 0 | Drop-Down List | 1, 2, 3, 4, 5 | 1 | 1= N/A or 0
| 3.3.1 Residual Risk (B) Likelihood | ScrResRiskLik | 0 | Drop-Down List | 1, 2, 3, 4, 5 | 1 | 1= N/A or 0

## (Admin) (hidden)
Drop-Down Lists:
| Dept List (General Fund) | Dept List - Short | Fund List | Fund List - Short | Project Rationale | Project Size | Life Cycle | YesNo List | YesNoUnknown List | YesNoNA List | Criteria Scale | Criteria Scale NA | ImpactUnknown List | ImpactNA List | Options List | NewExistingAsset | BusCaseStatus | Dept List (All Funds)
| N/A | - | Water | WTR | Increase LOS | S | Acquire/Create/Upgrade | Yes | Yes | Yes | 1 | 1 | Positive (+) | Positive (+) | Option 1 | Existing Asset | Active | N/A
| Admin & IT | ADMN | Wastewater | WWR | Maintain LOS - Same Capacity | M | Operations & Maintainance | No | No | No | 2 | 2 | Negative (-) | Negative (-) | Option 2 | New Asset | Archived | Admin & IT
| Recreation | RECR | Electrical | ELC | Increased Capacity (Growth) | L | Renewal |  | Unknown | NA | 3 | 3 | Mixed (+ & -) | Mixed (+ & -) | Option 3 |  | Budgeted | Recreation
| Parks | PRKS | General | GRL |  | XL | Disposal |  |  |  | 4 | 4 | Unknown | NA |  |  |  | Parks
| Facilities | FACL | [8 empty] | 5 | 5 | [5 empty] | Facilities
| Fleet | FLET | [9 empty] | NA | [5 empty] | Fleet
| Fire | FIRE | [15 empty] | Fire
| Emergency Response | EMRS | [15 empty] | Emergency Response
| Works | WRKS | [15 empty] | Works
Water
Wastewater
Electrical
Misc
| Version: | v1
| Lock Sheet P/W: | lock
| Fund | General
| Fiscal Year | 2022
Project Code
|  | [Fiscal Year] | [Fund] | [Dept (if appl)] | [Short Proj Name]
|  | 2022 | GRL | Check Department Selection | -
Finance
| DISCOUNT RATE: | 5%

## (Export) (hidden)
ProjFileNam | FileNam | FiscalYr | Fund | DiscRate | ProjNam | ProjDept | ProjStrtDate | ProjDur | ProjSize | ProjRat | StatProj | StatDescCmpl | StatGate1Aprv | StatBCCmpl | StatGate2Aprv | StatPrReady | StatGate3Aprv | StatBusCase | FnCPXPCNPC | FnCPXPCYr1 | FnCPXPCYr2 | FnCPXPCYr3 | FnCPXPCYr4 | FnCPXPCYr5 | FnCPXEFNPC | FnCPXEF1 | FnCPXEF2 | FnCPXEF3 | FnCPXEF4 | FnCPXEF5 | FnCPXMLNPC | FnOPXRCNPC | FnOPXOMNPC | FnTLCNPC | CrIncLOSLOI | CrIncLOSBOI | CrMtnLOSSCCon | CrMtnLOSSCLik | CrMtnLOSSCCrit | CrMtnLOSICLON | CrMtnLOSICCrit | CrCompCon | CrCompLik | CrHSICons | CrHSILik | CrHSISca | CrRslcy | CrLCFI | CrCBEnvLOI | CrCBEnvBOI | CrCBSocLOI | CrCBSocBOI | CrCBEconLOI | CrCBEconBOI | CrGHGReduc | SCrIntResLOI | ScrResRiskCon | ScrResRiskLik | ProjDesc | Contact | ProjLoc | SustainCoBen | GrntFund | ProjInterdep | StratInit | AssetReplace | EcologicImp | LOIIntRes | ProjPurp | NewAsset? | UsefulLife | UsefulLifeRem | Version:
| 2021-Water_BusCase_Template | 2022 | GRL | 5% |  | N/A | 2021-01-01 |  |  |  | Project Description Incomplete | No | No | No | No | No | No | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Unknown | Unknown | Unknown | Unknown | Unknown | 0 |  | 0 | 0 | 0 | v1